## MVP Backlog
Epic | Feature | Story | Priority | Depends On | Acceptance
Foundation | CLI | Implement `deviq run` command | High | - | CLI executes pipeline
Foundation | Configuration | Load deviq.yaml | High | CLI | Configuration precedence respected
Foundation | Pipeline | Implement ExecutionPipeline | High | Configuration | Pipeline orchestrates execution
Evidence | Collectors | Git Evidence Collector | High | Pipeline | Commits collected
Evidence | Collectors | Filesystem Collector | High | Pipeline | File changes collected
Evidence | Correlation | Evidence Graph | High | Collectors | Relationships created
Analysis | Session | Session Reconstruction | High | Evidence Graph | DevelopmentSession generated
Analysis | Knowledge | Knowledge Extraction | High | Session | KnowledgeBase generated
Analysis | Metrics | Metrics Engine | Medium | Knowledge | MetricsReport generated
Analysis | Contribution | Effective Contribution | Medium | Metrics | Contribution report generated
Reporting | Reports | Executive Summary | High | Analysis | Markdown report generated
Reporting | Recommendations | Recommendation Engine | High | Knowledge;Metrics | RecommendationPackage generated
Platform | API | REST API v1 | Medium | Reporting | Endpoints available
Platform | SDK | Plugin SDK | Medium | Pipeline | Plugins load dynamically